## Risk Register
Risk ID | Risk Description | Asset / Process | Threat | Likelihood | Impact | Inherent Risk | Existing Controls | Residual Risk | Treatment | Risk Owner | Due Date | Status
R-001 | Excessive user access may allow unauthorised access to sensitive systems or information. | User Access Management | Unauthorised or inappropriate access | 4 | 4 | 16 | Quarterly access reviews; role-based access; joiner/mover/leaver procedures | 8 | Mitigate | IT Security | 2026-10-31 | Open
R-002 | Compromise of a privileged account could allow an attacker to gain administrative access to critical systems. | Privileged Access | Phishing; credential theft; account compromise | 3 | 5 | 15 | MFA; privileged account controls; access reviews | 5 | Mitigate | IAM / IT Security | 2026-10-31 | In Progress
R-003 | A critical supplier security weakness could expose organisational systems or sensitive information. | Supplier Management | Third-party security failure | 3 | 5 | 15 | Supplier due diligence; security questionnaires; contractual security requirements | 10 | Mitigate | Procurement / Security | 2026-11-30 | Open
R-004 | Unpatched vulnerabilities may be exploited to compromise systems or applications. | Vulnerability Management | Exploitation of known vulnerabilities | 4 | 5 | 20 | Vulnerability scanning; patch management; remediation tracking | 10 | Mitigate | Security Operations | 2026-10-15 | In Progress
R-005 | Sensitive information could be disclosed through inappropriate access, insecure processes or accidental sharing. | Data Protection | Data leakage or accidental disclosure | 3 | 5 | 15 | Access controls; security awareness; data handling procedures | 10 | Mitigate | Data Protection / Security | 2026-11-30 | Open
R-006 | Insufficient security monitoring could delay detection and response to malicious activity. | Security Monitoring | Undetected security incident | 3 | 4 | 12 | Centralised logging; security monitoring; incident response procedures | 6 | Mitigate | Security Operations | 2026-11-15 | In Progress
R-007 | AI systems may produce inappropriate, inaccurate or unauthorised outputs or process information inappropriately. | AI Governance | AI misuse; inappropriate AI output; data exposure | 3 | 4 | 12 | AI use-case inventory; human oversight; AI risk assessment | 8 | Mitigate | AI Governance | 2026-12-15 | Open
R-008 | Employees may fall victim to phishing or other social engineering attacks due to insufficient security awareness. | Security Awareness | Phishing; social engineering | 4 | 3 | 12 | Security awareness training; phishing simulations; reporting procedures | 6 | Mitigate | HR / Security | 2026-11-30 | In Progress
Risk Rating Reference
Risk Score | Risk Rating
1–4 | Low
5–9 | Medium
10–15 | High
16–25 | Critical
Risk Calculation
Likelihood × Impact = Risk Score
Identifies key information security and governance risks, including the affected process, threat, likelihood, impact, existing controls, residual risk, treatment approach, ownership and target dates.

## Risk Matrix
Risk Matrix
Provides a consistent method for calculating and rating risk using likelihood and impact. The resulting risk score is mapped to Low, Medium, High or Critical risk levels.
Likelihood / Impact | 1 | 2 | 3 | 4 | 5
5 Almost Certain | 5 | 10 | 15 | 20 | 25
4 Likely | 4 | 8 | 12 | 16 | 20
3 Possible | 3 | 6 | 9 | 12 | 15
2 Unlikely | 2 | 4 | 6 | 8 | 10
1 Rare | 1 | 2 | 3 | 4 | 5
Risk Rating
Risk Score | Risk Rating
1–4 | Low
5–9 | Medium
10–15 | High
16–25 | Critical

## Risk Treatment
Risk Treatment
Documents how identified risks will be managed, including the current treatment approach, rationale, planned actions, responsible owner, target date and remediation status.
Risk ID | Current Treatment | Treatment Rationale | Planned Action | Risk Owner | Target Date | Status
R-001 | Mitigate | Existing access controls reduce the likelihood of excessive access, but evidence gaps remain. | Strengthen quarterly access certification and require documented application-owner approval. | IT Security | 2026-10-31 | Open
R-002 | Mitigate | MFA and privileged access controls reduce the likelihood of account compromise. | Review privileged accounts and investigate any MFA exceptions. | IAM / IT Security | 2026-10-31 | In Progress
R-003 | Mitigate | Supplier security controls reduce exposure but current assessments are incomplete. | Complete security assessments for high-risk suppliers and track remediation actions. | Procurement / Security | 2026-11-30 | Open
R-004 | Mitigate | Vulnerability scanning identifies weaknesses, but remediation timelines require monitoring. | Prioritise critical vulnerabilities and track remediation against defined timeframes. | Security Operations | 2026-10-15 | In Progress
R-005 | Mitigate | Access controls and data handling procedures reduce the likelihood of data leakage. | Review sensitive-data access and strengthen data handling awareness. | Data Protection / Security | 2026-11-30 | Open
R-006 | Mitigate | Centralised logging and monitoring provide detection capability. | Review monitoring coverage and validate alert escalation procedures. | Security Operations | 2026-11-15 | In Progress
R-007 | Mitigate | AI governance controls provide oversight but some AI use cases require further assessment. | Complete AI risk assessments and document human oversight requirements. | AI Governance | 2026-12-15 | Open
R-008 | Mitigate | Security awareness training reduces exposure to phishing and social engineering. | Conduct phishing simulations and provide targeted training for higher-risk users. | HR / Security | 2026-11-30 | In Progress
Disclaimer:
This risk treatment register contains simulated risks and fictional data created for learning purposes. It does not represent an assessment of a real organisation.